## Introduction
This spreadsheet was developed to help in planning the effort required for various implementation scenarios.
If the Emergency Department includes a separate trauma area with a different workload, then the effort hours
for the project manager and hospital staff are much greater. One implementation during the CMS grant
estimated that it added 250-300 hours to the implementation.

## Details
Effort Hours Projections for Four Scenarios
Scenario #1: New ePCR/New HIE-EMS Connector/New Non-Epic EMR | [6 empty] | eg AMR Meds or ImageTrend or Zoll or ESO or et al/Mirth-based HIE/Cerner
Basically this is the original Grant. If this is your configuration, contact Mark Branning 858.395.7946 to discuss.
The original Grant was for ~350,000 and another $115,000 In-kind.
Scenario #2: New ePCR/New HIE-EMS Connector/Existing hospital running Epic EMR | [7 empty] | (duration estimated at 6-9 months)
|  | ePCR vendor |  | HIE with an EMS interface engine(4) |  |  |  | ED/Epic EMR |  |  | Agency |  |  | LEMSA(5)
| PM | Technical(2) | Test/Install(3) | PM(4) | Technical | Test/Install(3) | PM | Technical | Others(1) | PM(6) | Test | Training(7) | PM | Technical | Testing
| 30 | 130 | 15 | 450 | 550 | 50 | 15 | 85 | 28 | 20 | 15 | 0.5 hr/medic | no est | no est | no est
Scenario #3: Add a new Epic ED to an existing ePCR/HIE/Epic configuration | [7 empty] | (duration 2-3 months)
|  | ePCR |  | HIE with an EMS interface engine(4) |  |  |  | ED/Epic EMR |  |  | Agency |  |  | LEMSA(5)
| PM | Technical(2) | Testing | PM | Technical | Test/Install(3) | PM | Technical | Others(1) | PM(6) | Test | Training(7) | PM | Technical | Testing
| 5 | 2 | 5 | 60 | 5 | 5 | 15 | 85 | 28 | 10 | 5 | email only | no est | no est | no est
Scenario #4: Add a new EMR to an existing ePCR/HIE/other EMR configuration | [7 empty] | (duration estimated at 3-6 months)
|  | ePCR vendor |  | HIE with an EMS interface engine(4) |  |  |  | ED/Epic EMR |  |  | Agency |  |  | LEMSA(5) |  |  | EMR Vendor
| PM | Technical(2) | Test/Install(3) | PM(4) | Technical | Test/Install(3) | PM | Technical | Others(1) | PM(6) | Test | Training(7) | PM | Technical | Testing | PM | Technical | Test/Install
| 5 | 2 | 15 | 240 | 200 | 50 | 200 | 160 | 28 | 20 | 15 | email only | no est | no est | no est | 60 | 240 | 40
(1) see Epic resource listing for details
(2) Technical includes interfaces and changes to the product's UI/workflow
(3) Technical development and Testing overlap
(4) In all installs, assumption is the HIE PM is the overall PM
(5) Although no attempt was made to estimate effort by a LEMSA, at a minimum, consider testing of eOutcomes from the ePCR to the LEMSA. In SD, the LEMSA was involved on workgroups,
but had no direct deliverables; they did, however, remove some obstacles and were very visible and supportive during Go-Live.
(6) Coordination and communication tasks regarding paramedics and fire.
(7) some cases there is true training, some cases just communication that another ED is live
Note on I20: SD Health Connnect: 100 develop 60 install/test
Note on R20: SD Health Connnect: 120 core product 120 install